## Sheet1
Area | Place | Scene | Duration | Time | Status | Description | Climbing Gym | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11
Luohu | Kingkey 100 | Long Shot | 10 ～ 30s | After 7pm, before 8pm | Planning | Need be careful about the net signal and image signal | Blue Sky Luohu A | bar: 2021-06-10
| The Mixc in Luohu | Full Shot | 10 ~ 30s | Before 10pm | Done |  | Blue Sky Luohu B | bar: 2021-05-28
Nanshan | Tencent Building | Full Shot | 10 ~ 30s | After 7pm, before 8pm | Planning | Be careful of the buildings and the guards | Nerd Cave | bar: 2021-06-07
| Overpass Bridge | Full Shot | 10 ~ 30 | Before 10pm | Planning | Delayed by raining storm | TT | bar: 2021-05-31 to 2021-06-02
| Hanking Building | Full Shot | 10s | Before 7.15pm | Planning | Delayed by raining storm | TT | bar: 2021-05-31 to 2021-06-02
| Huarun Building | Full shot | 10 ~ 30s | Before 5.30 am | Done | bar: 2021-05-28
|  | Full shot | 10 ~ 30s | Before 5.20 am | Planning | bar: 2021-06-07
|  | Full shot | 10 ~ 30s | after 7 pm, before 8pm | Planning |  | TT | bar: 2021-06-09
| Shenkang Station | Full Shot | 10 ~ 30s | After 7pm, before 8pm | Done | bar: 2021-05-27
| Shenzhen Bay Bridge | Full Shot | 10 ～ 30s | Before 5.30 | Done | bar: 2021-05-27
|  | Full Shot | 10 ～ 30s | after 7 pm, before 8pm | Planning |  | TT | bar: 2021-06-08
Futian | Pingan Building | Full Shot | 10 ~ 30s | Before 5.30 am | Planning | bar: 2021-06-09
| Pingan Building | Full Shot | 10 ~ 30s | after 7 pm, before 8pm | Planning |  | Blue Sky Futian | bar: 2021-06-10
| Pingan Building From the costal side | Full Shot | 10 ~ 30s | before 5.30am, betweeen 6.20 ~ 7.00 | Planning | bar: 2021-06-08