## July
Project | Module | Section | Item | 2020-07-24 | 2020-07-25 | 2020-07-26 | 2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31
Nextop Front-End | Finance | Accounting Policy | List Page | bar: 2020-07-24; 2020-07-27
Create And Update Page | bar: 2020-07-27
|  | Accounting Book | List Page | bar: 2020-07-28
Create And Update Page | bar: 2020-07-28
|  | Accounting Chart Item | List Page | bar: 2020-07-29
Create And Update Chart | bar: 2020-07-29
Create And Update Chart Item | bar: 2020-07-30
Asign Chart | bar: 2020-07-30 to 2020-07-31
| Bug | Fix Can't not find module | bar: 2020-07-31
| Construction | Got Docker env | bar: 2020-07-29
Handle Nginx Proxy Issue | bar: 2020-07-31

## August
Project | Module | Item | Piority | Status | 2020-08-01 | 2020-08-02 | 2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09 | 2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30 | 2020-08-31
Nextop Front-End | Development | Accounting Policy Self-Test | P0 | Done | bar: 2020-08-03
|  | Accounting Book Self-Test | P0 | Done | bar: 2020-08-03
|  | Accounting Chart Item Self-Test | P0 | Done | bar: 2020-08-03
|  | Change Finance UI | P2 | bar: 2020-08-17; 2020-08-27
|  | UI QA | P0 | Done | bar: 2020-08-17
|  | Menu Icon | P0 | bar: 2020-08-17
|  | UI Change(height of logo, thrid-child menu item, menu icon) | P0 | bar: 2020-08-19
|  | Accounting Calendar Development | P0 | bar: 2020-08-10 to 2020-08-12
|  | Cost development | P0 | bar: 2020-08-18
|  | Cost BE | P1 | bar: 2020-08-18 to 2020-08-19
|  | Supplementary development | P0 | bar: 2020-08-14; 2020-08-17
|  | Supplementary BE | P1 | bar: 2020-08-17 to 2020-08-18
|  | Calendar part QA | P0 | bar: 2020-08-20
|  | Calendar Integration With BE | P0 | Done | bar: 2020-08-12 to 2020-08-14
|  | Statement Development | P0 | bar: 2020-08-25 to 2020-08-28; 2020-08-31
|  | Book/Chart/Policy Integration with BE | P0 | Done | bar: 2020-08-04 to 2020-08-07
|  | Book/Chart/Policy QA | P0 | Done | bar: 2020-08-08; 2020-08-10 to 2020-08-14; 2020-08-17 to 2020-08-22; 2020-08-24 to 2020-08-28
| Bug | Book/Chart/Policy Integration with BE | P1 | Done | bar: 2020-08-06
|  | Clear double main page tag | P0 | bar: 2020-08-06; 2020-08-12
|  | Debugger Element UI | P2 | bar: 2020-08-12
|  | clear redundancy branch | P2 | bar: 2020-08-12
|  | Fix Switch Tenant doesn't refesh menu | P0 | bar: 2020-08-12
|  | Searchbox Change Router can not hightlight Menubar | P0 | Done | bar: 2020-08-11
|  | Add new Route refresh page 404 | P0 | bar: 2020-08-06; 2020-08-11
|  | FE Deployment knowledge sharing conference | P0 | bar: 2020-08-08; 2020-08-14; 2020-08-17
| Construction | Change Project File Structure | P0 | Done | bar: 2020-08-06
|  | Fix Docker cannot proxy nginx issue | P2 | bar: 2020-08-10; 2020-08-19
|  | Change UI basic layout | P0 | Done | bar: 2020-08-05; 2020-08-08
|  | Handle Nginx Proxy Issue | P1 | Done | bar: 2020-08-04
FE Foundation | Tools | Set alias for git-flow | P2 | Done | bar: 2020-08-08

## September
Project | Module | Item | Piority | Status | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30
Nextop Front-End | Finance | Transaction Development | P0 | bar: 2020-09-01 to 2020-09-03
| Common | UI Style: Always show one Screen(Autocomplete the background) | P1
|  | Static Server Development | P1 | bar: 2020-09-04
|  | Refresh Page when Window Size Change | P0
|  | the Horizontal Scrollbar of Table should be wider | P1
|  | Add catch exception in AvueRouter(not null) | P2
|  | Validator of Table Form( 1. auto increase height when error hint, 2.Hint user one by one by using message dialogue) | P1
|  | Table Scrollbar Will Occurred Offset When change columns | P2
|  | Page Cache | P0
|  | Documentations: Project Structure | P1
|  | Global UI Component | P2
|  | Clean Useless Node Package | P2

## October
Module | Item | Piority | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31
Common | Page cache | P2
| Clear page error | P2 | bar: 2020-10-26
UI | Table | P0 | bar: 2020-10-12 to 2020-10-14
| Global search input | P0 | bar: 2020-10-19
| Logo | P1 | bar: 2020-10-19
| Tab | P0 | bar: 2020-10-21
| Fix dashboard default active | P1 | bar: 2020-10-24
| Add 1280 min width | P1 | bar: 2020-10-24
| Change Finance Basic informations' UI | P0 | bar: 2020-10-22
| Hover Show Operation Icon | P0 | bar: 2020-10-26
| Change Menubar Icon(Second) | P1 | bar: 2020-10-30
| Fix the delay when resize window | P0 | bar: 2020-10-24
| Add custom width of Search Input | P2 | bar: 2020-10-24
| Scrollbar | P1 | bar: 2020-10-22
| Menubar | P0 | bar: 2020-10-20 to 2020-10-21
| Fix remained bugs of common | P2 | bar: 2020-10-27
| UI Test | P1 | bar: 2020-10-22 to 2020-10-24
Other | Vue3 sharing conference | P1 | bar: 2020-10-24
Bugs | When switch tenant, should clear the menu item | P1
| When close the last one tag, should clear the selected menu Item | P1

## November
Module | Items | Piority | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29 | 2020-11-30
Component | Toolbar Custom Component | P0 | bar: 2020-11-02 to 2020-11-03
Common | Add checked status in Vantop-Table | P0 | bar: 2020-11-03
| Add refresh logic into Vantop-Table | P1 | bar: 2020-11-03
| Discuss remain bug with UI | P0 | bar: 2020-11-03
| Check advanced filter unpop prob | P0 | bar: 2020-11-04
| Fix remain bugs in UI | P1 | bar: 2020-11-04
| Extract UI lib into vantop-ui project | P0 | bar: 2020-11-09
| router view's scroball should not effect container | P1
| Vantop-Table Overflow probs | P1 | bar: 2020-11-25
| Add reset icon in select input | P0
| Make routes dynamically inject | P0 | bar: 2020-11-26
| FE cli | P2 | bar: 2020-11-21
| Fix new UI prob | P1 | bar: 2020-11-24
| Finish operation system static pages | P2
| Fix global BUG | P1 | bar: 2020-11-12
| Fix ui BUG | P1 | bar: 2020-11-11
| Reconstruct-vantop-table-storage | P0 | bar: 2020-11-06
| Vxe-table drag line offset | P1
| Rewrite vantop-cli with TS | P2
| Extract Vantop Table Remote Storage func to Project only | P0 | bar: 2020-11-18; 2020-11-25
| Overflow prob issued by Zehao | P1
| Fix btn group | P0 | bar: 2020-11-05
| Imigrate UI lib to ERP project and Test it simply | P0 | bar: 2020-11-18
Fix customer part press browser back btn | bar: 2020-11-05
Finance | Change finance basic info section's UI | bar: 2020-11-10
Operation System | Build the structure of OS | P1 | bar: 2020-11-19
Others | NodeJs sharing conference | P0 | bar: 2020-11-07
| Made a example of psql in Node.js | P1 | bar: 2020-11-03 to 2020-11-05
| Documentate the UI Lib | P0 | bar: 2020-11-16
Advanced | Make UI documentation onlinilly | P0 | bar: 2020-11-17
| Propoganda UI-Lib in teamwide | P1 | bar: 2020-11-23

## December
Module | Items | Piority | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05 | 2020-12-06 | 2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2020-12-13 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31
UI | Table probs | P0 | bar: 2020-12-01 to 2020-12-02
| 新增 <NoData> "暂无数据" 公共组件 | P2
| Finish Increasement component | P1 | bar: 2020-12-28
| Add create btn component | P1 | bar: 2020-12-24
| Fixed refresh page, vantop-popover component disappeared | P2
Operation System | Finish static pages | P0
ERP | Clear useless file | P1 | bar: 2020-12-14 to 2020-12-15
| Fresh data when switch tenant | P1 | bar: 2020-12-14 to 2020-12-15
| Finish Review Modules | P0 | bar: 2020-12-28
Others | Test SSH | P2
| Discuss Business logic component completetation | P1
| Changelog of ui-lib | P2
| Regulartion of Folder, Coding | P1
| Organize the shortages of ERP | P0
User Experience Improvement | webpack cache problems | P0
| Extract Third-Party as cdn | P0

## Jan.
Module | Items | Piority | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12 | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19 | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26 | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30
UI | Fix the remian probs of ui | P1
| taliwind css, negotiate with UI(css variables) | P1
ERP | Route will vaguely compare | P1
| Keep Alive Page | P0
| Improve webpack performance | P0
| webpack cache problems | P0
Others | Research why npm publish could enable without build | P0
| Adjust documentations | P1
| Add husky hooks into each package | P2
| Improve webpack performance | P1
| Research lerna automatic deployment | P2
| Added no-empty slot into table | P0
| Remove Avue | P0
| Finish logout | P0
| Finish tag list animation | P0
| Finish seprate main application and subchild application | P0
| Find the reason why dashboard will insert to the last of tag list in ERP | P2
| Add tag beside the actived tag | P2
| Adapt font size in different screens | P2
| Responsive layout | P1
| columns draggable | P2

## Feb.
Module | Items | Priority | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31
UI | columns draggable | P1
| make a sortable example | P0
| Integrate sortable demo in Ui Lab | P0
| Adapt font size in different screens | P2
| Add animation of draggable columns | P1
| taliwind css, negotiate with UI(css variables) | P1
FE Lab | Input Component | P0 | bar: 2021-03-15 to 2021-03-19
| Fix Css build prob | P0 | bar: 2021-03-25
| Think about the icon prob | P0 | bar: 2021-03-25
| Button Component | P1
| Select Component | P1
| Add pack ui lib process | P0 | bar: 2021-03-23
| Add husky hooks into each package | P2
ERP | Add tag beside the actived tag | P1
| Research the consum of swtich different application in Qiankun | P0 | bar: 2021-03-22
| Fix dynamic route setting | P0
| Responsive layout | P1
Others | Code Review | P0
| Draggable Columns doesn't show correctly solution | P2
| Dicuss the browser version with Product Manager(Linheng Zhang) | P0
| Discuss the sharing salon wth Jianzhong | P1
| Create a vue-base demo of Tailwind | P0
| Migrate Tailwind into Micro Application | P0

## April
Module | Items | Priority | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30
UI | Finish upload page logic development | P0 | bar: 2021-04-09
| Finish result dialogue | P0 | bar: 2021-04-08
Research BE upload logic | bar: 2021-04-08
Finish result be logic | bar: 2021-04-12
Add exception deal | bar: 2021-04-12
Add documentation | bar: 2021-04-12
Test import component | bar: 2021-04-13 to 2021-04-14
Figure out where store the new style rules | bar: 2021-04-13
| Add JS Variables | P1 | bar: 2021-04-13
| Add CSS Variables | P1 | bar: 2021-04-13
| Add changelog to Nextop Business | P2 | bar: 2021-04-13
| Add same file limit to Import Dialogue | P0 | bar: 2021-04-15
| Change the whole color of ERP | P0 | bar: 2021-04-14
Fix the remain problems of color in ERP
| Add Select Component | P1 | bar: 2021-04-19
| Make a plan for Element version | P0 | bar: 2021-04-16
| Make paln in zbox | P0 | bar: 2021-04-19
| Finish Button | P0 | bar: 2021-04-21
| Build valement | P1 | bar: 2021-04-19
Fe Lab | Fix the pop-droplist change table header's height(Raised by Jianzhong) | P0 | bar: 2021-04-21
Micro Web | Research BE upload logic(???) | P0

## May
Module | Items | Priority | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31
Button | Change Icon size | P0 | bar: 2021-05-10
| Add multiple size of Iconed Button | P1 | bar: 2021-05-10
| Button Test | P0 | bar: 2021-05-11
| Button uI test | P1 | bar: 2021-05-12
| Replace icons | P1 | bar: 2021-05-11 to 2021-05-12
| Add pop hint when icon button | P0 | bar: 2021-05-12
| Drop button | P1 | bar: 2021-05-19
Input | View status | P0 | bar: 2021-05-11
| Add input clearable hover status | P0 | bar: 2021-05-11
| Add mutiple suffix choices | P0 | bar: 2021-05-11
| Add search input | P0 | bar: 2021-05-11
| Combine search input | P0 | bar: 2021-05-13
| Add empty text show | P1 | bar: 2021-05-13
| Success, error status | P0
| Select search input | P1 | bar: 2021-05-19
Select | Select size | P0 | bar: 2021-05-13
| Add mutiple select count | P0 | bar: 2021-05-18
| Borderless | P0 | bar: 2021-05-18
| Group Styles | P0 | bar: 2021-05-18
| Select Create | P0 | bar: 2021-05-18
| Overflow show ellipsis | P0 | bar: 2021-05-19
| add max width of dropdown | P0 | bar: 2021-05-20
| Figure out show ellipsis of li | P0 | bar: 2021-05-20
| Set option width | P0 | bar: 2021-05-24
| With icon(Cancelled) | P2
Tag | Development | P1 | bar: 2021-05-17
| Modify documents | P1 | bar: 2021-05-18
| Fix style of info | P0 | bar: 2021-05-19
| Make a tooltip of ellipsis | P0 | bar: 2021-05-20
Tab | Adjust basic style | P0 | bar: 2021-05-21
| Adjust docs | P0 | bar: 2021-05-21
| Add disabled status | P0 | bar: 2021-05-24
| More | P1 | bar: 2021-05-21
Dialogue | Adjust basic style | P0 | bar: 2021-05-22
| Modify documents | P0 | bar: 2021-05-22
Drawer | Modify basic style | P0 | bar: 2021-05-22
| Modify documents | P0 | bar: 2021-05-22
Tooltip and Popover | Modify tooltip basic style | P0 | bar: 2021-05-22
| Modify tooltip docs | P0 | bar: 2021-05-22
| Modify popover basic style | P0 | bar: 2021-05-22
| Discuss whether we need triangle or not | P0 | bar: 2021-05-24
| Finish Popover animation | P0 | bar: 2021-05-24
| Modify popover docs | P0 | bar: 2021-05-22
| Modify Popconfirm basic style | P0 | bar: 2021-05-22
Alert | Discuss dark mode style | P1 | bar: 2021-05-24
| Modify alert style | P0 | bar: 2021-05-22
| Add alert icons | P0 | bar: 2021-05-22
Avatar | Adjust basic style | P0 | bar: 2021-05-22
| add status | P2
Color Picker | Add hue panel | P2
Figure out why element can complie MD file as html

## Vanlement Plan
Module | Items | Priority | Costing
Global | 修改主色调以及辅色调 | P0 | 2hr
| 样式打包调研 | P0 | 4hr
| 打包发布至npm测试 | P1 | 4hr
| 替换至erp内测试 | P1 | 4hr
Button | 修改Border-Radius、边距、尺寸等外观样式 |  | 1hr
| 修改交互行为样式 |  | 4hr
| 修改不同状态的样式显示 |  | 4hr
| 添加扩展组件（按钮组、图标按钮组、上下翻页按钮） |  | 2hr
| 测试 |  | 3hr
| 文档编写 |  | 1hr
| 修改UI提出的问题 |  | 4hr
Input | 修改交互行为样式 |  | 2hr
| 基础外观样式修改 |  | 2hr
| 添加清空按钮交互动画以及增强视觉效果 |  | 4hr
| 前缀输入框实现 |  | 2hr
| 后缀输入框实现 |  | 2hr
| 复制操作输入框实现 |  | 1hr
| 编辑操作输入框实现 |  | 2hr
| 测试 |  | 2hr
Select Input | 下拉搜索基本样式实现 |  | 4hr
| 下拉搜索功能实现 |  | 4hr
| 无边框下拉搜索实现 |  | 2hr
| 组合搜索框样式实现 |  | 4hr
| 组合搜索框测试 |  | 2hr
| 下拉搜索框整体测试 |  | 2hr

## Climber
Module | Item | Priority | Hours | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31
FE | Read the UI lib docs | P1 | 1hr
| Read all the mini-program demos | P1 | 2hr
| Start page FE coding | P0 | 2hr | bar: 2021-05-02
| Login and Register Page | P0 | 2hr | bar: 2021-05-02 to 2021-05-03
| Change city coding | P1 | 1hr | bar: 2021-05-02
| Gym List | P0 | bar: 2021-05-02
| Post page FE coding | P0 | 4hr | bar: 2021-05-02
BE | API docs | P0 | 2hr
| API coding | P1 | 4hr | bar: 2021-05-03
Deployment | Test | bar: 2021-05-03
Publish | bar: 2021-05-05
UI Design | Make sketch designs | P0 | 3hrs
| Logo | P0 | 15min

## June
Module | Items | Priority

## July 2021
Module | Items | Desc | Priority | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31
FE Basement | Update system of Service worker detective automatically | Webwork, import a hash name file to trigger update set a timer to check whether it has updated or not | P0 | bar: 2021-07-09; 2021-07-12
UI Library | Fix problem issued by ZJ |  | P0 | bar: 2021-07-09